## Project Plan
Template provided by |  |  |  | Last updated: | 2024-02-05
For more templates visit: envivesolutions.com/resources
Activity | Start Date | Finish Date | Percentage Complete | Assigned To | Dependencies/Notes
Initiation
Planning
Execution / Monitoring & Controlling
Closing

## Sample Plan v1
Intensive Outpatient Program Implementation |  |  |  | Last updated: | 2023-07-15
Notes: • This is not a complete plan and only an example to illustrate how this project plan can be used. • This version separates project activities by formal project phases (in green cells). These are not required. See version 2 for another way to organize your project.
Activities | Start Date | Finish Date | Percentage Complete | Assigned To | Dependencies/Notes
Initiation
Determine budget for opening IOP
Determine IOP model
MILESTONE: Project approved by leadership
Resources
Assign Project Manager | 2023-02-01 | 2023-02-07 | 100% | Heather
Assign team members | 2023-02-01 | 2023-02-07 | 100% | Heather
Project Manager
Planning
Project Management
Meet with team to create project plan | 2023-02-10 | 2023-02-10
Schedule regular project status meetings
Scope
Create Scope Document
Scope Document Signed
Staffing
Determine staffing needs | 2023-02-15 | 2023-04-01 | 100% | Sylvia
Marketing
Define marketing strategy | 2023-05-01 | 2023-05-15 | 100% | Michael
Execution
Apply for IOP license with state
Determine who are SMEs for compiling information for application. | 2023-02-08 | 2012-02-10 | 100% | Heather
Staffing
Post job openings | 2023-06-12 | 2023-06-21 | 50% | Sylvia
Marketing
Closing
Meet to document lessons learned with team
Celebrate new program!

## Sample Plan v2
Intensive Outpatient Program Implementation |  |  |  | Last updated: | 2023-06-01
Notes: • This is not a complete plan and only an example to illustrate how this project plan can be used. • This version separates project activities by sample categories (in green cells). These are not required. See version 1 for another way to organize your project using formal project phases.
Activities | Start Date | Finish Date | Percentage Complete | Assigned To | Dependencies/Notes
Determine budget requirements for IOP | 2023-01-17 | 2023-01-31 | 100% | Sherrie L.
Determine IOP model | 2023-01-23 | 2023-01-31 | 100% | Joy H.
Market research on need and viability
Research reimbursements
Application
Gather information for application | 2023-02-01 | 2023-05-26 | 100% | Joy H.
Submit application | 2023-05-30 | 2023-05-30 | 100% | Joy H.
MILESTONE: Application Approved | 2023-08-31 | 2023-08-31 |  | Joy H.
Location
Research potential locations | 2023-06-01 | 2023-07-31 | 75% | Joseph S.
Compile list of potential contractors | 2023-06-26 | 2023-07-14 | 100% | Joseph S.
Determine permits needed
Project Management
Assign Project Manager | 2023-09-01 | 2023-09-01 |  | Joy H. | Dependent on application being approved.
Assign team members | 2023-09-01 | 2023-09-08 |  | Joy H.
Create Scope Document | 2023-09-05 | 2023-09-12
Scope document approved | 2023-09-12 | 2023-09-14
Create project plan | 2023-09-14 | 2023-11-01
Schedule regular project status meetings
Meet with team to review project risks
Meet to document lessons learned with team |  |  |  |  | Middle and end of project
Human Resources
Staffing
Determine staffing needs | 2023-02-15 | 2023-04-01 | 100% | Maria O.
Create policies and procedures
Create onboarding materials
Create job descriptions
Post job openings
Marketing
Define marketing strategy | 2023-05-01 | 2023-05-15 | 100% | Michael
Develop list of referral sources
Official Opening
Schedule date for ribbon cutting event
Celebrate new program!

## How to Use Project Plan
Template provided by
For more templates visit: envivesolutions.com/resources
How to Use this Project Plan Template
1 | Review Sample Plan tabs to familiarize yourself with how this template might be used. In our sample plan we have used opening an Intensive Outpatient Program. However, project plans can be used for any project.
2 | Column headings: • Activity - Use this column to list activities related to your project. Use formatting and colors to distinguish between groups of activities (e.g. bold text, colored cells, etc.) Activities typically are bigger deliverables and often take weeks or months to complete. Smaller tasks should be listed on the task list (e.g. scheduling a meeting or emailing someone for information). • Start date (when will you start this activity) - An activity could take 10 hours total, but those hours could be spread over weeks or even months. Being able to see these dates "on paper" allows you to see dependencies more clearly and get a realistic view of the timeline. It also helps to prioritize and better allocate resources. You can also make adjustments based on the availability of resources. (For example - staff being out on vacation.) • Finish Date (when do expect to finish?) - This includes the amount of time needed to complete the task, but also accounts for the availability of resource and "lag time" where resource needs to wait on other components to be complete. • Percent complete - Monitor progress with a percentage. Using 25%, 50%, 75%, 100% is great! Don't get hung up on making it exact. You just want to show progress. (As you go along it is time for a happy dance as you rack up all those 100%s!) • Assigned To - This could be the actual resource OR the person who oversees that resource. Try to list just one name as ultimately accountable. • Dependencies/Notes - Your space to note anything you are waiting on (dependency) or other notes. For example: Activity is delayed as the assigned employee recently quit and you need to determine how to handle.
3 | Row headings: Sample Plan v1 - Formal Project Phases • Initiation: Where project is authorized or given a "green light." Budget and team members are allocated, and the project officially begins! • Planning: Every project needs planning to be successful. • Execution/Monitoring & Controlling: This is where the work is getting done, it is tracked and status, risks and issues are regularly reviewed. • Closing: This is where you call it complete and operationalize. Activities under "Closing" include a lessons learned session, a final meeting to review that all activities are complete and of course celebrating your success! NOTE: You do not have to use the headings above. Sample Plan V2 provides another example. Organize your project plan how it best suits you, your team and your project.
4 | Customize! Please use this template and adjust columns and colors to suit you and your project.