## RISKS
Template provided by | [8 empty] | Date last updated: | 2022-08-01
For more templates visit: envivesolutions.com/resources
Item # | Description of Potential Risk | Category | Date Entered | Date of Last Review | Owner | Likelihood 1=Low 2=Significant 3=High | Impact 1=Low 2=Marginal 3=High | Color Code | Mitigation | Notes | Status | Date Closed
1 | SAMPLE ITEM: XYZ department is not able to collaborate | Resources | 2022-03-01 |  | Lisa | 1 | 3 | 3 | Will adjust scope of project so that those department resources are not needed. |  | Open
2 | SAMPLE ITEM: Key Subject Matter Expert may be leaving company | Resources | 2022-03-01 |  | Laurie | 2 | 2 | 4 | If SME leaves, will have them train other staff on where to find project documentation. |  | Open
3 | SAMPLE ITEM: Grant application period falls during time of many competing priorities, which may result in lack of quality of application or missed deadline and therefore not being awarded. | Time | 2022-01-15 |  | Janet | 2 | 3 | 6 | All staff will be enlisted to complete various components. Various tasks in process will be reprioritized so that grant is main focus. Worst case: Will put project on hold if necessary and seek funding elsewhere. | Grant application submitted on time. | CLOSED | 2022-08-01
4 | SAMPLE ITEM: May start using new project management tools after project starts, which may cause disruption | Tools | 2022-04-01 |  | Mario | 1 | 1 | 1 | If project manager thinks it will cause too much disruption, will continue to use existing tools for this project. |  | Open
5 | [7 empty] | 0
6 | [7 empty] | 0
7 | [7 empty] | 0
8 | [7 empty] | 0
9 | [7 empty] | 0
10 | [7 empty] | 0
11 | [7 empty] | 0
12 | [7 empty] | 0
13 | [7 empty] | 0
14 | [7 empty] | 0
15 | [7 empty] | 0
16 | [7 empty] | 0
17 | [7 empty] | 0
18 | [7 empty] | 0
19 | [7 empty] | 0
20 | [7 empty] | 0

## ASSUMPTIONS
Template provided by |  |  |  |  | Date last updated: | 2022-05-01
For more templates visit: envivesolutions.com/resources
ITEM # | CATEGORY | DESCRIPTION OF ASSUMPTION | OWNER | DUE DATE | ACTIONS TO VALIDATE THE ASSUMPTIONS | STATUS | NOTES
1 | Stakeholders | SAMPLE ITEM: All departments are going to be functional and cooperative. | Megan | 2022-02-28 | Megan to send one-page acknowledgement of terms of collaboration on project to department heads for signature. | In progress | 2/15/22: 2 of 3 departments have signed off. Megan meeting with third department next Friday to resolve.
2 | Tools | SAMPLE ITEM: New project tools will be effective and easy to use. | Jennie | 2022-03-05 | Additional training will be provided and available over next three months. | Closed | 4/15/22: Tools are in use with little to no issues.
3 | Resources | SAMPLE ITEM: IT department will allocate resources to project. | James | 2022-03-05 | James meeting with IT Dept director to address resource needs and confirm resources. | Closed
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21

## ISSUES
Template provided by | [7 empty] | Date last updated: | 2022-04-20
For more templates visit: envivesolutions.com/resources
Item # | Description of Issue (Current and needs to be resolved now) | Category | Date Added | Date to be resolved by | Owner/Resource | Impact 1=Low 2=Marginal 3=High | Action | How it was resolved | Status | Date Closed
1 | SAMPLE ITEM: Brandon (key IT SME) is on unexpected medical leave | Resources | 2022-04-01 | 2022-04-07 | James | 3 | 4/2: James to reach out to IT dept. lead to see if another resource in his department can step in. If this is not an option, he will seek out a temporary employee. | 4/7: IT dept reassigned a resource to this project. | CLOSED | 2022-04-07
2 | SAMPLE ITEM: Some additional partners are missing from focus groups | Needs/Gaps Assess. | 2022-04-10 | 2022-05-01 | Megan | 2 | 4/12: Compiling list of contacts to call to arrange additonal focus groups.
3
4
5
6
7
8
9
10
11
12
13
14
15

## DECISIONS
Template provided by
[5 empty] | Date last updated: | 2022-04-20
For more templates visit: envivesolutions.com/resources
Item # | CATEGORY | DECISION | REASON FOR DECISION | CONSULTED | DATE | NOTES
1 | Scope | SAMPLE ITEM: If XYZ department cannot participate in project will adjust scope of project, but continue. | Project aligns with company's goals for this year and is a priority with or without XYZ Department. That department's involvement can be phased in later. | Project sponsor: Lily, project team | 2022-03-01
2 | Resources | SAMPLE ITEM: If IT department cannot assign another resource, will hire a temp. | Because of high priority of project and availability of funds, this option would allow for less disruption to project and timeline. | Project sponsor: Lily | 2022-04-01
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## How to Use RAID LOG
Template provided by
For more templates visit: envivesolutions.com/resources
1 | What does RAID mean? R=Risks: Risks are things that could happen during the course of a project, but haven't happened yet. A=Assumptions: What are you assuming about this project? These are very helpful to uncover and determine if your assumptions are correct. Team may also realize some action steps are needed to validate the assumption. I=Issues: Issues are what is happening now and can be a problem, an inconsistency, or a conflict. D=Decisions: What decisions did you make along the way that affected the project?
2 | Risk Log • By regularly reviewing and documenting potential risks, the project manager and the team are more aware of threat and prepared for how to mitigate should risk become an issue. • The color coding is set to happen automatically on this template. The lowest number based on on impact and likelihood are green and highest numbers are red. Mid-range level risks will be on a spectrum of greenish yellow to yellow to red-orange. The colors help to prioritize project risks and give an overview of entire project's viability. • Some risks may close as there is no longer a risk. Some may close because the risk is happening and has been moved to "Issues" tab. Once an item is no longer a risk, it is marked closed and you may choose to format those cells as gray. Do not delete the risk. This is legacy documentation and may provide helpful reminders when conducting the project lessons learned session upon close of project.
3 | Assumptions • At minimum, the project team needs to brainstorm for assumptions during the project's planning phase. If project is complex and lengthy (e.g. spanning more than a year), it is beneficial for the team to spend some time brainstorming again to bring any assumptions to the surface. • The project manager regularly reviews list of assumptions and follows up on any outstanding action items.
4 | Issues • By regularly reviewing and documenting issues, project manager and the team are aware of the status, road blocks and any additional action steps needed. • The color coding is set to happen automatically on this template based on the number entered. The lowest impact issues are green and highest impact issues are red. Mid-range issues yellow. The colors help to prioritize project issues and give an overview of entire project's viability. • Items on this list are closed once they are resolved. Once an item is no longer an issue, it is marked closed and you may choose to format those cells as gray. Do not delete the issue. This is legacy documentation and may provide helpful reminders when conducting the project lessons learned session upon close of project.
5 | Decisions • A decision log is a beneficial communication tool to ensure that all stakeholders are aware of how a decision was reached, what other options were considered, and who is accountable for the decision. It also provides guidance to the team members and can eliminate potential confusion.