## RISKS
Template provided by | [8 empty] | Date last updated: | 2024-02-05
For more templates visit: envivesolutions.com/resources
Item # | Description of Potential Risk | Category | Date Entered | Date of Last Review | Owner | Likelihood 1=Low 2=Significant 3=High | Impact 1=Low 2=Marginal 3=High | Color Code | Mitigation | Notes | Status | Date Closed
1 | SAMPLE ITEM: Application is not approved by state |  | 2023-02-05 |  | Anna P. | 1 | 3 | 3 | If application is not approved, Joy and Sherrie will contact BHSD to see if it can be updated and resubmitted. |  | Open
2 | SAMPLE ITEM: Key Subject Matter Expert may be leaving company | Resources | 2023-03-01 |  | Joy H. | 2 | 2 | 4 | SME is updating all documentation and agreed to stay to train new staff. |  | Open
3 | SAMPLE ITEM: Grant funding is not awarded. | Budget | 2023-02-01 |  | Sherrie L. | 2 | 3 | 6 | Joy and Sherrie to see other grant funding. However, will delay project. | Grant awarded. | CLOSED | 2023-03-01
4 | SAMPLE ITEM: Finding enough staff to open. | Resources | 2023-03-01 |  | Maria O. | 1 | 2 | 2 | Will have some staff at main location support operations temporarily. Maria to research job fairs to recruit staff. |  | Open
5 | [7 empty] | 0
6 | [7 empty] | 0
7 | [7 empty] | 0
8 | [7 empty] | 0
9 | [7 empty] | 0
10 | [7 empty] | 0
11 | [7 empty] | 0
12 | [7 empty] | 0
13 | [7 empty] | 0
14 | [7 empty] | 0
15 | [7 empty] | 0
16 | [7 empty] | 0
17 | [7 empty] | 0
18 | [7 empty] | 0
19 | [7 empty] | 0
20 | [7 empty] | 0

## ASSUMPTIONS
Template provided by |  |  |  |  | Date last updated: | 2024-02-05
For more templates visit: envivesolutions.com/resources
ITEM # | CATEGORY | DESCRIPTION OF ASSUMPTION | OWNER | DUE DATE | ACTIONS TO VALIDATE THE ASSUMPTIONS | STATUS | NOTES
1 | Time | SAMPLE ITEM: IOP application will be approved by state or be able to be resubmitted with corrections in a timely manner. | Sherrie L. | 2023-08-01 | Sherrie to request meeting with BHSD contact to check in address questions and concerns | Closed | Application approved.
2 | Tools | SAMPLE ITEM: Construction will begin on time and be complete within 30 days of target date. | Joseph S. | 2023-11-01 | Joseph to meet regularly with construction companies project manager for updates. | In progress
3 | Resources | SAMPLE ITEM: IT department will allocate resources to project. | Ben L. | 2023-03-05 | Ben meeting with IT Dept director to address resource needs and confirm resources.
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21

## ISSUES
Template provided by | [7 empty] | Date last updated: | 2022-04-20
For more templates visit: envivesolutions.com/resources
Item # | Description of Issue (Current and needs to be resolved now) | Category | Date Added | Date to be resolved by | Owner/Resource | Impact 1=Low 2=Marginal 3=High | Action | How it was resolved | Status | Date Closed
1 | SAMPLE ITEM: Brandon (key SME) is on unexpected medical leave | Resources | 2023-04-01 | 2023-04-15 | Joy H. | 3 | 4/2: Sherrie to attend project meetings while Brandon is out. | 4/7: Sherrie was able to attend meetings and provide input until Brandon's return. | CLOSED | 2022-04-07
2 | SAMPLE ITEM: Project budget will not cover all planned staffing needs. | Budget | 2023-09-01 | 2023-09-14 | Joy H. | 2 | 8/5: Staffing plan being reworked to stay within budget. |  | Open
3
4
5
6
7
8
9
10
11
12
13
14
15

## DECISIONS
Template provided by
[5 empty] | Date last updated: | 2023-04-15
For more templates visit: envivesolutions.com/resources
Item # | CATEGORY | DECISION | REASON FOR DECISION | CONSULTED | DATE | NOTES
1 | Resources | SAMPLE ITEM: Sherrie to attend project meetings while key SME is out on medical leave. | Waiting for SME would delay project timeline. | Sherrie L., Joy H., Anna P. | 2023-04-03
2 | Staffing | SAMPLE ITEM: Due to budget constraints a medical prescriber will not be hired initially. Will reconsider six months after opening. | Review of project budget, revealed budget had to be re-aligned. | Sherrie L., Joy H., Michael S. | 2023-09-22
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## How to Use RAID LOG
Template provided by
For more templates visit: envivesolutions.com/resources
1 | What does RAID mean? R=Risks: Risks are circumstances that COULD happen during the course of a project that could impact the project either negatively or positively. A=Assumptions: What are you assuming about this project? These are very helpful to uncover and determine if your assumptions are correct. Team may also realize some action steps are needed to validate the assumption. I=Issues: Issues are circumstances that are happening now and impacting the project. D=Decisions: What decisions did you make along the way that affected the project?
2 | Risk Log • By regularly reviewing and documenting potential risks, the project manager and the team are more aware of potential threats and prepared for how to mitigate should risk become an issue. • The color coding is set to happen automatically on this template. The lowest number based on impact and likelihood are green and highest numbers are red. Mid-range level risks will be on a spectrum of greenish yellow to yellow to red-orange. The colors help to prioritize project risks and give an overview of entire project's viability. • Some risks may close if it is no longer a risk. Some may close because the risk is happening and has been moved to "Issues" tab. Once an item is no longer a risk, it is marked closed and you may choose to format those cells as gray. Do not delete the risk. This is legacy documentation and may provide helpful reminders when conducting the project lessons learned session upon close of project.
3 | Assumptions • At minimum, the project team needs to brainstorm for assumptions during the project's planning phase. If the project is complex and lengthy (e.g. spanning more than a year), it is beneficial for the team to spend some time brainstorming again to bring any assumptions to the surface. • The project manager regularly reviews list of assumptions and follows up on any outstanding action items to validate the assumption.
4 | Issues • By regularly reviewing and documenting issues, the project manager and the team are aware of the status, road blocks and any additional action steps needed. • The color coding is set to happen automatically on this template based on the number entered. The lowest impact issues are green and highest impact issues are red. Mid-range issues yellow. The colors help to prioritize project issues and give an overview of entire project's viability. • Items on this list are closed once they are resolved. Once an item is no longer an issue, it is marked closed and you may choose to format those cells as gray. Do not delete the issue. This is legacy documentation and may provide helpful reminders when conducting the project lessons learned session upon close of project.
5 | Decisions • A decision log is a beneficial communication tool to ensure that all stakeholders are aware of how a decision was reached, what other options were considered, and who is accountable for the decision. It also provides guidance to the team members and can eliminate potential confusion.